## Timeline
ECOMMERCE PROJECT TIMELINE
PROJECT TITLE | ECOMMERCE | [6 empty] | LEGEND
PROJECT MANAGER | Joseph Cuartero | [7 empty] | To Do
In Progress
Done
FEATURES | TASK |  | ASSIGNED TO | PRIORITY | STATUS | PROGRESS | JANUARY |  |  |  |  | FEBRUARY | [15 empty] | MARCH
[7 empty] | 25 | 26 | 27 | 28 | 29 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 26 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26
BUYER FEATURES | Manage My Account
|  | Login | Joseph Pateña | High | DONE | 100% | bar: JANUARY 25
|  | Signup | Joseph Pateña | High | IN PROGRESS | 90% | bar: JANUARY 25
|  | Overview | Joseph Pateña | High | IN PROGRESS | 95% | bar: JANUARY 26
|  | My Profile | Joseph Pateña | High | IN PROGRESS | 95% | bar: JANUARY 26
|  | Address Book | Joseph Pateña | High | DONE | 100% | bar: JANUARY 26
|  | Manage Orders | Joseph Pateña | High | DONE | 100% | bar: FEBRUARY 5; MARCH 8 to MARCH 9
|  | Track package | Joseph Pateña | High | DONE | 100% | bar: MARCH 9
|  | My Payment Options | Joseph Pateña | High | TODO | 0%
|  | My Returns | Joseph Pateña | High | TODO | 0%
|  | My Cancellations | Joseph Pateña | High | TODO | 0%
|  | My wishlist | Joseph Pateña | High | DONE | 100% | bar: MARCH 1
|  | My reviews | Joseph Pateña | High | DONE | 100% | bar: FEBRUARY 17
|  | My Followed Store | Joseph Pateña | High | DONE | 100% | bar: MARCH 2
Homepage
|  | Product list | Joseph Pateña | High | DONE | 100% | bar: JANUARY 27; FEBRUARY 22
|  | Categories | Joseph Pateña | High | DONE | 100% | bar: JANUARY 27; FEBRUARY 22
|  | Recent Products | Joseph Pateña | High | DONE | 100% | bar: FEBRUARY 15; FEBRUARY 19
|  | Flash Sale | Joseph Pateña | High | DONE | 100% | bar: MARCH 3
|  | Featured Store | Joseph Pateña | High | DONE | 100% | bar: MARCH 4
|  | Item Filters | Joseph Pateña | High | DONE | 100% | bar: JANUARY 27; FEBRUARY 22
|  | Item Search | Joseph Pateña | High | DONE | 100% | bar: JANUARY 27; FEBRUARY 23
|  | Just for you | Joseph Pateña | High | DONE | 100% | bar: FEBRUARY 15; FEBRUARY 19
|  | Quick look | Joseph Pateña | High | DONE | 100% | bar: FEBRUARY 15; FEBRUARY 18
|  | Add to cart | Joseph Pateña | High | DONE | 100% | bar: FEBRUARY 15; FEBRUARY 18
Product Details
|  | Add to cart | Joseph Pateña | High | DONE | 100% | bar: JANUARY 27; FEBRUARY 22
|  | Add to wishlist | Joseph Pateña | High | DONE | 100% | bar: FEBRUARY 23
|  | Social sharing | Joseph Pateña | High | TODO | 0%
|  | Image preview | Joseph Pateña | High | TODO | 0%
|  | Product selling price | Joseph Pateña | High | DONE | 100% | bar: JANUARY 27
|  | Product variants, sizes & colors | Joseph Pateña | High | DONE | 100% | bar: JANUARY 27
|  | Product description | Joseph Pateña | High | DONE | 100% | bar: JANUARY 27
|  | Product ratings | Joseph Pateña | High | DONE | 100% | bar: FEBRUARY 17; FEBRUARY 19
|  | Question about the products | Joseph Pateña | High | DONE | 100% | bar: FEBRUARY 16
Shoppingcart
|  | Index | Joseph Pateña | High | DONE | 100% | bar: JANUARY 27
|  | Select and unselect | Joseph Pateña | High | DONE | 100% | bar: JANUARY 28
|  | Update qty | Joseph Pateña | High | DONE | 100% | bar: JANUARY 28
|  | Remove from cart | Joseph Pateña | High | DONE | 100% | bar: JANUARY 28
|  | Add to wishlist | Joseph Pateña | High | TODO | 0%
|  | Out of stock item | Joseph Pateña | High | DONE | 100% | bar: MARCH 5
|  | Estimate shipping | Joseph Pateña | High | DONE | 100% | bar: FEBRUARY 23 to MARCH 24
Checkout
|  | Delivery Information | Joseph Pateña | High | DONE | 100% | bar: FEBRUARY 1 to FEBRUARY 2
|  | Order summary | Joseph Pateña | High | DONE | 100% | bar: FEBRUARY 3
|  | Voucher discount | Joseph Pateña | High | DONE | 100% | bar: FEBRUARY 3; MARCH 5
|  | Shipping and billing | Joseph Pateña | High | DONE | 100% | bar: FEBRUARY 4
|  | Payment Options | Joseph Pateña | High | IN PROGRESS | 10% | bar: FEBRUARY 5
| Seller store |  | Joseph Pateña
|  | Homepage | Joseph Pateña | High | DONE | 100% | bar: MARCH 4
|  | Store profile | Joseph Pateña | High | DONE | 100% | bar: MARCH 4
|  | Products from store | Joseph Pateña | High | DONE | 100% | bar: MARCH 4
|  | Follow store | Joseph Pateña | High | DONE | 100% | bar: MARCH 4
|  | Voucher discount coupon | Joseph Pateña | High | DONE | 100% | bar: MARCH 5
|  | Social sharing | Joseph Pateña | High | TODO | 0%
SELLER FEATURES | Manage Products
|  | Add | Joseph Pateña | High | DONE | 100% | bar: FEBRUARY 8 to FEBRUARY 9
|  | Update | Joseph Pateña | High | DONE | 100% | bar: FEBRUARY 10
|  | Delete | Joseph Pateña | High | DONE | 100% | bar: FEBRUARY 11
|  | Question about the products | Joseph Pateña | High | DONE | 100% | bar: FEBRUARY 16
|  | Product ratings | Joseph Pateña | High | DONE | 100% | bar: FEBRUARY 16
Manage Store
|  | Store information | Joseph Pateña | High | TODO | 0%
|  | Manage store reviews | Joseph Pateña | High | TODO | 0%
|  | Shipping Settings |  | High | DONE | 100% | bar: MARCH 26
Orders
|  | Order management | Joseph Pateña | High | DONE | 100% | bar: FEBRUARY 15; MARCH 8 to MARCH 9
|  | Delivery proof | Joseph Pateña | High | DONE | 100% | bar: FEBRUARY 15; MARCH 9
|  | Track package timeline | Joseph Pateña | High | DONE | 100% | bar: FEBRUARY 15; MARCH 8 to MARCH 9
|  | Cancelled orders | Joseph Pateña | High | TODO | 0%
|  | Print shipping label | Joseph Pateña | High | DONE | 100% | bar: FEBRUARY 16
|  | Return orders | Joseph Pateña | High | TODO | 0%
Promotions
|  | Vouchers coupon | joseph Pateña | High | DONE | 100% | bar: MARCH 1
Shipping Settings
|  | Store shipping settings | Joseph Pateña | High | DONE | 100% | bar: MARCH 2
ADMIN FEATURES | Address
|  | Countries: Import | Joseph Pateña | High | DONE | 100% | bar: FEBRUARY 1 to FEBRUARY 2
|  | Province/State: Import | Joseph Pateña | High | DONE | 100% | bar: FEBRUARY 1 to FEBRUARY 2
|  | Town/City: Import | Joseph Pateña | High | DONE | 100% | bar: FEBRUARY 1 to FEBRUARY 2
Shipping
|  | Shipping Settings |  | High | DONE | 100% | bar: FEBRUARY 23 to MARCH 24
Categories
|  | Dynamic Categories |  | High | DONE | 100% | bar: FEBRUARY 22
|  | Add edit delete |  | High | DONE | 100% | bar: FEBRUARY 22